## ProductBacklog
PRODUCT BACKLOG
			Happy2Shop
SPRINT BACKLOG	US ID	BACKLOG ITEM			PRIORITY	RESPONSIBLE	ESTIMATE DATE	REMARKS
		AS A/AN	I WANT TO	SO THAT

1	SB1/US1	Customer	Register Myself Using Google + Account	I Can Receive A Confirmation Mail
	SB1/US1	Customer	Receive A Confirmation Mail	I Can Verify My Details
		Customer	Receive A Verification Mail	I Can Access The Happy2Shop portal
		Customer	Register Myself Using Facebook Account	I Can Access The Happy2Shop portal
1	SB1/US3	Customer	Login Into The System Using Google Account	I Can View/Edit My Profile
		Customer	Login Into The System Using Facebook Account	I Can View/Edit My Profile
		Customer	View The Account Details	I Can Modify My Account Details
		Customer	View The Previous Order Details	I Can TrackMy Recent Orders
		Customer	Update The Profile Details	I Can Update Profile Photo, Name
1	SB1/US4	Customer	View The Various Products	I Can See The Different Category Product
1	SB1/US5	Customer	Acess the QR scanner	I Can Scan The Products
		Customer	Modify The Account Password	I Can Keep My Account Secure
		Customer	Give Feedback/Suggestions	The Way Of Working Of The Happy2Shop Portal Can Be Improved
		Customer	Discuss Among Other Customers	I Can Share My Experience
		Customer	View My Shopping Cart List	I Can Buy Multiple Products at once
		Customer	View My Wish List	I Can Keep A Check On My Favorite Products
		Customer	View The Shopping Category	I Can See The Different Products Easily
		Customer	View The Payment Methods	I Can Manage My Payment
		Customer	See The Client of Happy2Shop	I Can Find the Stores Which Uses this Platform
		Customer	Add A Payment Method	I Can Find The Various Payment Services
		Customer	See The Filter Options	I Can Access The Product With Ease
		Customer	Remove The Itmes From Cart	I Can Checkout The Products
		Customer	View The List Of Products	I Can Sort the Products in Different Orders

## SprintBacklog_1
SPRINT BACKLOG 1

US ID	USER STORY	TASK ID	TASKS	TM	STATUS (NOT STARTED / IN PROGRESS / COMPLETED)	ESTIMATED DATE OF TASK COMPLETION

SPRINT 1 - <Digital College>
SB1/US1		SB1/D1/T1
		SB1/D1/T2
		SB1/D1/T3
		SB1/D1/T4
		SB1/D1/T5
		SB1/D1/T6
SB1/US2		SB1/D2/T1
		SB1/D2/T2
		SB1/D2/T3
		SB1/D2/T4
		SB1/D2/T5
SB1/US3		SB1/D3/T1
		SB1/D3/T2
		SB1/D3/T3
		SB1/D3/T4
SB1/US6		SB1/D4/T1
		SB1/D4/T2
		SB1/D4/T3
		SB1/D4/T4
		SB1/D4/T5
SB1/US7		SB1/D5/T1
		SB1/D5/T2
		SB1/D5/T3
		SB1/D5/T4
SB1/US27		SB1/D6/T1
		SB1/D6/T2
		SB1/D6/T3
		SB1/D6/T4
		SB1/D6/T5
SB1/US27		SB1/D7/T2
		SB1/D7/T3
		SB1/D7/T4
		SB1/D7/T5
SB1/US150		SB1/D8/T1
		SB1/D8/T2
		SB1/D8/T3
		SB1/D8/T4
SB1/US28		SB1/D9/T1
		SB1/D9/T2
		SB1/D9/T3
		SB1/D9/T4
		SB1/D9/T5
SB1/US50		SB1/D10/T1
		SB1/D10/T2
		SB1/D10/T3
		SB1/D10/T4
		SB1/D10/T5
SB1/US53		SB1/D11/T2
		SB1/D11/T3
		SB1/D11/T4
		SB1/D11/T5
SB1/US55		SB1/D12/T1
		SB1/D12/T2
		SB1/D12/T3
		SB1/D12/T4
SB1/US51		SB1/D13/T1
		SB1/D13/T2
		SB1/D13/T3
		SB1/D13/T4
		SB1/D13/T5
SB1/US70		SB1/D14/T1
		SB1/D14/T2
		SB1/D14/T3
		SB1/D14/T4
		SB1/D14/T5
SB1/US71		SB1/D15/T2
		SB1/D15/T3
		SB1/D15/T4
		SB1/D15/T5
SB1/US72		SB1/D16/T1
		SB1/D16/T2
		SB1/D16/T3
		SB1/D16/T4

## SB_Hours_01
Sprint Backlog 1

S. No.	User Story	Tasks	T M	Status	Days Left in Sprint
					Hours
EPIC-III : Final Deployment Of Project
1	As a developer I want to develop the hardware so that Wii-mote can be placed on the screen	Search about the hardware setup
		Search about components required
		Purchase component from Market
		Develop the hardware
2	As a developer I want to search for applications to be developed so that I can identify an application to be developed	Search annotation application
		search paint application
		search video making application
		search audio recording applications
3	As a developer I want to study about the technology to be used so I can identify the technology for application	Study tutorials
		Study tutorials
		start with Basics of c#
		start with Basics of c#
4	As a developer I want to begin coding in swings so I can start with designing of the application	start with Basics of c#
		start with Basics of c#
		coding of onscreen application					0
		coding of onscreen application					0
5	As a developer I want to start coding of my application so that I can develop application	coding of onscreen application					0
		coding of onscreen application					0
		Debug the code
		Debug the code
6	As a developer I want to implement my designed application so that I can use it	Implentation of application on virtual screen.
		Implentation of application on virtual screen.
		Implentation of application on virtual screen.
		Implentation of application on virtual screen.
7	As a developer I will implement the final project in the classrooms so that system can be used by the users at college	Switch on the projector and set the projected screen
		Interface it with PC/laptop
		Switch on the projector and set the projected screen
		Interface it with PC/laptop
8	As a tester I will check the whole system implemented in classrooms so that final system could be tested	Callibrate WII remote with virtual screen
		Use different applications on the virtual screen
		Check the changes made at the virtual screen
		Checking if it is working effectively with the laptop and not damaged
9	As a developer I will prepare the final delivarables of the whole system so that I can give the entire system	Prepare all hardware deliverables
		Prepare all software deliverables
		Prepare a hardware & software guide
		Prepare a user manual & guide for the users
10	As a developer I want to give training to faculty & students so that they can interact with the system & use it	Giving information to users about the project
		Project demonstration
		Project demonstration
		Project to be operated by different users

	PG	Parth Gupta
	PK	Parv Khandelwal
	NG	Nicky Gupta
	PM	Pankaj Maheshwari

	Verified By:

	(Product Owner)

## SB_BD_Ch01
Spring Backlog 01 burn down chart

Date	Planned Total Task	Actual Incompleted Task
4 Sep 18	180	180		Tasks
12 Sep 18	120	180
11 Sep 18	80	180
14 Sep 18	56	180
16 Sep 18	15	180
18 Sep 18	5	180

					Days

## SprintBacklog_2
SPRINT BACKLOG 2

US ID	USER STORY	TASK ID	TASKS	TM	STATUS (NOT STARTED / IN PROGRESS / COMPLETED)	ESTIMATED DATE OF TASK COMPLETION

SPRINT 2 - <Digital College>
	Add Department	SB2/D1/T1	Designing the GUI	SP
		SB2/D1/T2	Connection with database to fetch the data	RA
		SB2/D1/T3	Testing of the module on localhost and then on server.	RA+SP+PB+RM
	Register TA into the application(using poornima email account)	SB2/D2/T1	Designing of GUI	PB
		SB2/D2/T2	Validating user input at client level	RM
		SB2/D2/T3	Validating user input at server level	SP
		SB2/D2/T4	Connection with Database to insert the record.	RA
		SB2/D2/T5	Testing of the module on localhost and then on server.	RA+SP+PB+RM
	TA Receiving Confirmation Email	SB2/D3/T1	Designing of Email(to be send)	PB
		SB2/D3/T2	Send Email via coding using the Mandrill App	SP
		SB2/D3/T3	Connection with database to update the status in the database.	RA
		SB2/D3/T4	Testing of the module on localhost and then on server.	RA+SP+PB+RM
	Register TO into the application(using poornima email account)	SB2/D4/T1	Designing of GUI	PB
		SB2/D4/T2	Validating user input at client level	RM
		SB2/D4/T3	Validating user input at server level	SP
		SB2/D4/T4	Connection with Database to insert the record.	RA
		SB2/D4/T5	Testing of the module on localhost and then on server.	RA+SP+PB+RM
	TO Receiving Confirmation Email	SB2/D5/T1	Designing of Email(to be send)	PB
		SB2/D5/T2	Send Email via coding using the Mandrill App	SP
		SB2/D5/T3	Connection with database to update the status in the database.	RA
		SB2/D5/T4	Testing of the module on localhost and then on server.	RA+SP+PB+RM
	Add Subject	SB2/D6/T1	Designing of GUI	PB
		SB2/D6/T2	Validating user input at client level	RM
		SB2/D6/T3	Validating user input at server level	SP
		SB2/D6/T4	Connection with Database to insert the record.	RA
		SB2/D6/T5	Testing of the module on localhost and then on server.	RA+SP+PB+RM
	Register Timetable Co-ordinator into the application	SB2/D7/T1	Designing of GUI	PB
		SB2/D7/T2	Validating user input at client level	RM
		SB2/D7/T3	Validating user input at server level	SP
		SB2/D7/T4	Connection with Database to insert the record.	RA
		SB2/D7/T5	Testing of the module on localhost and then on server.	RA+SP+PB+RM
	Timetable Co-ordinator Receiving Confirmation Email	SB2/D8/T1	Designing of Email(to be send)	PB
		SB2/D8/T2	Send Email via coding using the Mandrill App	SP
		SB2/D8/T3	Connection with database to update the status in the database.	RA
		SB2/D8/T4	Testing of the module on localhost and then on server.	RA+SP+PB+RM

## SB_Hours_02
Sprint Backlog 2

S. No.	User Story	Tasks	T M	Status	Days Left in Sprint
					Hours
EPIC-III : Final Deployment Of Project

	PG	Parth Gupta
	PK	Parv Khandelwal
	NG	Nicky Gupta
	PM	Pankaj Maheshwari

	Verified By:

	(Product Owner)

## SB_BD_Ch02
Spring Backlog 02 burn down chart

Date	Planned Total Task	Actual Uncompleted Task
25 Sep 17	177	177		Tasks
28 Sep 17	110	177
2 Oct 17	80	177
5 Oct 17	66	177
7 Oct 17	15	177
9 Oct 17	5	177
					0

					Days

## SprintBacklog_3
SPRINT BACKLOG 3

US ID	USER STORY	TASK ID	TASKS	TM	STATUS (NOT STARTED / IN PROGRESS / COMPLETED)	ESTIMATED DATE OF TASK COMPLETION

SPRINT 3 - <Digital College>

## SB_Hours_03
Sprint Backlog 3

S. No.	User Story	Tasks	T M	Status	Days Left in Sprint
					Hours
EPIC-III : Final Deployment Of Project

	PG	Parth Gupta
	PK	Parv Khandelwal
	NG	Nicky Gupta
	PM	Pankaj Maheshwari

	Verified By:

	(Product Owner)

## SB_BD_Ch03_
Spring backlog 3 Burnt Down chart

Date	Planned Total Task	Actual Uncompleted Task
16 Oct 18	120	120		Tasks
18 Oct 18	110	120
20 Oct 18	80	120
21 Oct 18	25	120
22 Oct 18	15	120
23 Oct 18	0	120
					0

					Days

## SprintBacklog_4
SPRINT BACKLOG 4

US ID	USER STORY	TASK ID	TASKS	TM	STATUS (NOT STARTED / IN PROGRESS / COMPLETED)	ESTIMATED DATE OF TASK COMPLETION

SPRINT 4 - <Digital College>

## SB_Hours_04
Sprint Backlog 4

S. No.	User Story	Tasks	T M	Status	Days Left in Sprint
					Hours
EPIC-III : Final Deployment Of Project

	PG	Parth Gupta
	PK	Parv Khandelwal
	NG	Nicky Gupta
	PM	Pankaj Maheshwari

	Verified By:

	(Product Owner)

## SB_BD_Ch04
Date	Planned Total Task	Actual Uncompleted Task
10 Jan 19	190	190		Tasks
11 Jan 19	110	190
12 Jan 19	80	190
13 Jan 19	25	190
14 Jan 19	15	190
15 Jan 19	0	190
							0

							Days